## MPP AP calculator
Enter total ESA Price | 1000000 | SME: | YES
Enter no. milestones | 2
Country | GB
Milestone | Name | Date | Milestone % | Milestone amount | Advance Payment: 35% | Offset Amount | Payments
[7 empty] | 350000 | 35%
MS1 | FAT | August 2019 | 50% | 500000 | 0% | 0 | 500000 | 50%
| - | October 2019 | 0% | 0 | 0% | 0 | 0 | 0%
| - | May 2020 | 0% | 0 | 0% | 0 | 0 | 0%
| - | July 2020 | 0% | 0 | 0% | 0 | 0 | 0%
MS2 | FR | Decmber 2020 | 50% | 500000 | 35% | 350000 | 150000 | 15%
|  |  |  | 1000000 |  | 350000 | 1000000
INSTRUCTIONS: | 1) Please adapt the entries in the yellow cells above
2) Please do not use more than 3 milestones per year!
3) The blue cells show the milestone amounts, the orange calculates the offset related to the Advance Payment (subtracted amounts from the payments) and the green shows the actual cashflow
4) This MPP AP calculator is for a single contractor project. In case of sub-contractors, the MPP AP calculator should be used for each single contractors, and the results of the relevant Final Tables integrated together
Rev.1.3 | 2019-05-20

## Final table
select right | select here below
| Milestone Description | Schedule Date | Amount in EUR | Country (ISO Code)
| MS1 - Upon successful FAT Review and the Agency’s acceptance of all related deliverables | August 2019 | 500000 | GB
< Table G.9.1 (to be inserted in the Final Proposal)
| MS2 - Final settlement: Upon the Agency’s acceptance of all deliverable items due under the Contract and the Contractor’s fulfilment of all other contractual obligations including submission of the Contract Closure Documentation | Decmber 2020 | 500000
| Total |  | 1000000
Advance payment(s) and other financial conditions:
select right | Prime (P) | Company Name | Entity Code | Country (ISO Code) | Advance Payment (in EUR) | Off-Set against | Off-set by (amount in EUR) | Condition for release of the Advance Payment (if applicable) | < Table G.9.2 (to be inserted in the Final Proposal)
| P |  |  | GB | 350000 | MS1 | 0 | After signature of the Contract by both parties
0
0
0
[6 empty] | MS2 | 350000
select here above

## % payment plans
Percentage payment plans
| 2 | 2N | 2YES | 2NO | 3 | 3N | 3YES | 3NO | 4 | 4N | 4YES | 4NO | 5 | 5N | 5YES | 5NO
| MS Payment Plan | MS name | AP Offset SME (35%) | AP Offset NOSME (20%) | MS Payment Plan | MS name | AP Offset SME (35%) | AP Offset NOSME (20%) | MS Payment Plan | MS name | AP Offset SME (35%) | AP Offset NOSME (20%) | MS Payment Plan | MS name | AP Offset SME (35%) | AP Offset NOSME (20%)
MS1 | 50% | FAT |  | 20% | 35% | BDR |  | 20% | 30% | BDR |  | 20% | 20% | BDR |  | 20%
MS2 |  | - |  |  | 30% | FAT | 15% |  | 20% | CDR | 10% |  | 20% | CDR | 10%
MS3 |  | - |  |  |  | - |  |  | 25% | SAT | 15% |  | 25% | FAT | 15%
MS4 |  | - |  |  |  | - |  |  |  | - |  |  | 15% | SAT | 5%
MS Final | 50% | FR | 35% |  | 35% | FR | 20% |  | 25% | FR | 10% |  | 20% | FR | 5%
Total | 100% |  |  |  | 100% |  |  |  | 100% |  |  |  | 100%
number of milestones
2
3
4
5
SME
YES
NO